## Work_Completion_Browse637502828
Work Completion Browse
Project : Jhansi Zone
From Date : 02/02/2021 To date: 02/02/2021
Page 1 of 1
Total Records: 30 Records 1 to 30
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 68608.1178 | 2021-02-05 11:48 | Completion of trial run and hand over to concern dept. | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22831326.1622 | Self Contracting
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 102912.1767 | 2021-02-05 11:48 | Other development works | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22797022.1033 | Self Contracting
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 102912.1767 | 2021-02-05 11:48 | Finishing works | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22797022.1033 | Self Contracting
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 102912.1767 | 2021-02-05 11:48 | Casting of roof slab of CWR | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22797022.1033 | Self Contracting
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 137216.2357 | 2021-02-05 11:48 | Up to first floor slab | 20 |  | 142 | 22899934.28 | 1900-01-01 | -22762718.0443 | Self Contracting
Civil lines CWR | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.055 | 12474203.242 | 171520.2946 | 2021-02-05 11:48 | Excavation of foundtion in every kind of rock ,foundation and floor slab of CWR | 25 |  | 142 | 22899934.28 | 1900-01-01 | -22728413.9854 | Self Contracting
Distribution Lines at Different zones Ph-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 2885.7805 | 2507.135 | 723504.1294 | 2021-02-05 11:51 | Completion of trial run | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22176430.1506 | Self Contracting
Distribution Lines at Different zones Ph-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 2885.7805 | 2507.135 | 723504.1294 | 2021-02-05 11:51 | Testing of pipe lines network including testing and commissioning | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22176430.1506 | Self Contracting
Distribution Lines at Different zones Ph-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 2885.7805 | 2507.135 | 723504.1294 | 2021-02-05 11:51 | After laying and jointing | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22176430.1506 | Self Contracting
Distribution Lines at Different zones Ph-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 2885.7805 | 2507.135 | 5064528.9057 | 2021-02-05 11:51 | Supply of pipes | 70 |  | 142 | 22899934.28 | 1900-01-01 | -17835405.3743 | Self Contracting
Feeder Main Phase-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 1053.156 | 9596.256 | 1010635.4584 | 2021-02-05 11:50 | Completion of trial run | 10 |  | 142 | 22899934.28 | 1900-01-01 | -21889298.8216 | Self Contracting
Feeder Main Phase-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 1053.156 | 9596.256 | 1010635.4584 | 2021-02-05 11:50 | Testing of pipe lines network including testing and commissioning | 10 |  | 142 | 22899934.28 | 1900-01-01 | -21889298.8216 | Self Contracting
Feeder Main Phase-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 1053.156 | 9596.256 | 1010635.4584 | 2021-02-05 11:50 | After laying and jointing | 10 |  | 142 | 22899934.28 | 1900-01-01 | -21889298.8216 | Self Contracting
Feeder Main Phase-1 | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 1053.156 | 9596.256 | 7074448.2088 | 2021-02-05 11:50 | Supply of pipes | 70 |  | 142 | 22899934.28 | 1900-01-01 | -15825486.0712 | Self Contracting
House Connection Ph-1 Jhansi | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 167.4864 | 4965.204 | 831604.1432 | 2021-02-05 11:52 | After Work Completion | 100 |  | 142 | 22899934.28 | 1900-01-01 | -22068330.1368 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 199935.3886 | 2021-02-05 11:42 | Completion of trial run and hand over to concern dept. | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22699998.8914 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 199935.3886 | 2021-02-05 11:42 | Other work & Commissioning | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22699998.8914 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 199935.3886 | 2021-02-05 11:42 | Piping work | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22699998.8914 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 299903.0828 | 2021-02-05 11:42 | Casting of tank, wall | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22600031.1972 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 399870.7771 | 2021-02-05 11:42 | Casting of bottom ring beam | 20 |  | 142 | 22899934.28 | 1900-01-01 | -22500063.5029 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 299903.0828 | 2021-02-05 11:42 | Staging up to bottom ring beam | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22600031.1972 | Self Contracting
OHT Civil lines | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 19993538.856 | 399870.7771 | 2021-02-05 11:42 | Foundation work | 20 |  | 142 | 22899934.28 | 1900-01-01 | -22500063.5029 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 37462.913 | 2021-02-05 11:46 | Completion of trial run and hand over to concern dept. | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22862471.367 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 37462.913 | 2021-02-05 11:46 | Other work & Commissioning | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22862471.367 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 37462.913 | 2021-02-05 11:46 | Piping work | 10 |  | 142 | 22899934.28 | 1900-01-01 | -22862471.367 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 56194.3695 | 2021-02-05 11:46 | Casting of tank, wall | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22843739.9105 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 74925.826 | 2021-02-05 11:46 | Casting of bottom ring beam | 20 |  | 142 | 22899934.28 | 1900-01-01 | -22825008.454 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 56194.3695 | 2021-02-05 11:46 | Staging up to bottom ring beam | 15 |  | 142 | 22899934.28 | 1900-01-01 | -22843739.9105 | Self Contracting
OHT Silvertganj | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.02 | 18731456.488 | 74925.826 | 2021-02-05 11:46 | Foundation work | 20 |  | 142 | 22899934.28 | 1900-01-01 | -22825008.454 | Self Contracting
Settling Tank Ph-1 Jhansi | Self Contracting | 4 | Jhansi Jhansi Water Supply Reorg. sch. Phase-1 | 0.1 | 16668520.751 | 1666852.0751 | 2021-02-05 11:52 | After Work Completion | 100 |  | 142 | 22899934.28 | 1900-01-01 | -21233082.2049 | Self Contracting