## Project_Work_Order6375117025402
Project Work Order
From 01 Jan 2000 To 13 Mar 2021
Page 1 of 1
Total Records: 114 Records 1 To 114
Project | WO No | Wo_Date | Contrator | Task Name | Labour Name | Qty | Rate | Amount | TaxAmt | Retaintion% | Bill Qty | Bal.Bill Qty | Bill Amount | Specification
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 300mm | 700 | 1040 | 728000 | 0 | 0 | 0 | 700 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 350mm | 1650 | 1040 | 1716000 | 0 | 0 | 0 | 1650 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 400mm | 1150 | 1040 | 1196000 | 0 | 0 | 0 | 1150 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 450mm | 25 | 1040 | 26000 | 0 | 0 | 0 | 25 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 500mm | 25 | 1040 | 26000 | 0 | 0 | 0 | 25 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 600mm | 930 | 1040 | 967200 | 0 | 0 | 0 | 930 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 700mm | 10 | 1040 | 10400 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 800mm | 10 | 1040 | 10400 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM PSC Pipe Carting & Laying of Pipe 900mm | 1270 | 1040 | 1320800 | 0 | 0 | 0 | 1270 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM PSC Pipe Carting & Laying of Pipe 1000mm | 10 | 1040 | 10400 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Reinstatement of all type road | 5000 | 900 | 4500000 | 0 | 0 | 0 | 5000 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-6 ELECTRICAL & MECHANICAL WORKS ON IPS-1 to IPS-9 | 1 | 123971240 | 123971240 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-7 ELECTRICAL & MECHANICAL WORKS ON MPS-1 & MPS-2 | 1 | 55489045 | 55489045 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP A.Desgin & Drawing | 1 | 8267359 | 8267359 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Foundation- for all structures of STP | 1 | 13778931 | 13778931 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Earth Filling of all structure | 1 | 7500000 | 7500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Stilling Chamber | 1 | 300000 | 300000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Screen Channels | 3 | 100000 | 300000 | 0 | 0 | 0 | 3 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Grit Chamber | 3 | 400000 | 1200000 | 0 | 0 | 0 | 3 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Common Channel | 1 | 500000 | 500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.S.B.R. Reactors | 4 | 49100000 | 196400000 | 0 | 0 | 0 | 4 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Chlorine Contact Tank | 1 | 4300000 | 4300000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Chlorination House | 1 | 800000 | 800000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Sludge Piping(SAS Pump - Sludge Sump) | 1 | 100000 | 100000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Sludge Sump | 1 | 1400000 | 1400000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Sludge Pump House | 1 | 5100000 | 5100000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Rising Main- Sludge PH to centrifuge | 1 | 100000 | 100000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Centrifuge House | 1 | 5100000 | 5100000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Piping-final effluent from CCT Outlet | 50 | 19500 | 975000 | 0 | 0 | 0 | 50 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Final Effluent Chamber | 1 | 300000 | 300000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Sludge Platform(Below Centrifuge H.) | 1 | 2700000 | 2700000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Blower/Control,Admin,Lab,Building | 1 | 27300000 | 27300000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Internal Water Supply | 1 | 800000 | 800000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Landscaping and horticulture work | 1 | 500000 | 500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Fire Fighting Arrangement | 1 | 435505 | 435505 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-8 C. E&M Supply | 1 | 231905000 | 231905000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-8 D.E&M-Erection,Installation,Testing&Commissioning | 1 | 12395448 | 12395448 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-9 Const-1no of office building(plinth area 445Sqm) | 1 | 9437786 | 9437786 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-9 residential build. type A-2Nos(plinth area 34.2Sqm) | 2 | 840364 | 1680728 | 0 | 0 | 0 | 2 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-9 residential build. type B-9nos(plinth area 45.6Sqm) | 9 | 1068046 | 9612414 | 0 | 0 | 0 | 9 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-9 residential build. type C-1nos(plinth area 62.7Sqm) | 1 | 1411104 | 1411104 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,G-9 residential building type D 1 no. (86.00 Sqm) | 1 | 1668969 | 1668969 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 600mm 8mm thick | 80 | 28004.95 | 2240396 | 0 | 0 | 0 | 80 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 700 mm 8 mm thick | 750 | 29712.6 | 22284450 | 0 | 0 | 0 | 750 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 800 mm 10 mm thick | 50 | 34223.55 | 1711177.5 | 0 | 0 | 0 | 50 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 900 mm 10 mm thick | 290 | 50193.35 | 14556071.5 | 0 | 0 | 0 | 290 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 1000 mm 10 mm thick | 950 | 52243.55 | 49631372.5 | 0 | 0 | 0 | 950 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 1100 mm 12 mm thick | 400 | 62388.3 | 24955320 | 0 | 0 | 0 | 400 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method with MS Pipe 1200 mm 12 mm thick | 150 | 64791.25 | 9718687.5 | 0 | 0 | 0 | 150 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 250 mm ID | 2150 | 11753.8 | 25270670 | 0 | 0 | 0 | 2150 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 300 mm ID | 1300 | 13362 | 17370600 | 0 | 0 | 0 | 1300 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 350 mm ID | 1380 | 17628.15 | 24326847 | 0 | 0 | 0 | 1380 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 400 mm ID | 50 | 18864.05 | 943202.5 | 0 | 0 | 0 | 50 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 450 mm ID | 1360 | 28578.7 | 38867032 | 0 | 0 | 0 | 1360 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS, HDD Method With HDPE Pipe 500 mm ID | 200 | 29814.6 | 5962920 | 0 | 0 | 0 | 200 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Supply&Const. of Precast MH (900X1650)mm Dia.depth | 60 | 21547.5 | 1292850 | 0 | 0 | 0 | 60 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Supply&Const. of Precast MH (1200X2300)mm Dia.depth | 170 | 73778.3 | 12542311 | 0 | 0 | 0 | 170 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Supply&Const. of Precast MH (1500X9000)mm Dia.depth | 56 | 202402 | 11334512 | 0 | 0 | 0 | 56 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Supply&Const. of Precast MH (1800X9000)mm dia.depth | 65 | 253635.75 | 16486323.75 | 0 | 0 | 0 | 65 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,In Depth variation of MH (900X1650)mm Dia.depth | 30 | 4968.25 | 149047.5 | 0 | 0 | 0 | 30 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,In Depth variation of MH (1200X2300)mm Dia.depth | 130 | 16791.75 | 2182927.5 | 0 | 0 | 0 | 130 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,In Depth variation of MH (1500X9000)mm Dia.depth | 30 | 26779.25 | 803377.5 | 0 | 0 | 0 | 30 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,In Depth variation of MH (1800X9000)mm dia.depth | 35 | 34238.85 | 1198359.75 | 0 | 0 | 0 | 35 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Dismentling of Interlocking tile road | 6550 | 87.21 | 571225.5 | 0 | 0 | 0 | 6550 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.M.C.C Room | 1 | 7100000 | 7100000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.D. G. Platform | 1 | 2900000 | 2900000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.HT Substation build. with Meter Room | 1 | 2700000 | 2700000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Transformer Yard | 1 | 1700000 | 1700000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Boundary Wall with Gates | 1 | 10000000 | 10000000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Watchman Hut | 2 | 400000 | 800000 | 0 | 0 | 0 | 2 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Internal Roads / Path ways | 1 | 2500000 | 2500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-8 STP,Civil-B.Internal Drainage | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Dismentling of BT road | 4200 | 97.16 | 408072 | 0 | 0 | 0 | 4200 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Dismentling of C.C. Road | 100 | 185.64 | 18564 | 0 | 0 | 0 | 100 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Reinstatememt of Interlocking tile road | 6465 | 604.35 | 3907122.75 | 0 | 0 | 0 | 6465 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Reinstatememt of BT road | 4157 | 1556.01 | 6468333.57 | 0 | 0 | 0 | 4157 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Reinstatememt of C.C. Road | 100 | 1332.46 | 133246 | 0 | 0 | 0 | 100 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Sup/Fab-300mm casing MS pipe-150mm HDPE carrier pip | 250 | 19141.75 | 4785437.5 | 0 | 0 | 0 | 250 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg2-EMS,Sup/Fab-300mm casing MS pipe-200mm HDPE carrier pip | 600 | 24141.36 | 14484816 | 0 | 0 | 0 | 600 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Project O&M cost for the Project | 1 | 90036000 | 90036000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Pipe Laying Network | 264246 | 2087.29 | 551558033.34 | 0 | 0 | 0 | 264246 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Nalah Tapping point | 14 | 517857.14 | 7249999.96 | 0 | 0 | 0 | 14 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Nalah Tapping Line Tranchless With MH incl. all | 1400 | 17971.43 | 25160002 | 0 | 0 | 0 | 1400 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Const.of MH | 12058 | 30530.23 | 368133513.34 | 0 | 0 | 0 | 12058 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Gully Pit | 4000 | 10800 | 43200000 | 0 | 0 | 0 | 4000 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Reinstatement of road & Pavment | 344140 | 728.47 | 250695665.8 | 0 | 0 | 0 | 344140 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-2 Const. of Sewer Connecting Chamber | 5287 | 18731.98 | 99035978.26 | 0 | 0 | 0 | 5287 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -01 (Chakkar ki Milak, 2.67 MLD) | 1 | 14200000 | 14200000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -02 (Chakkar ki Milak, 1.29 MLD) | 1 | 14200000 | 14200000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -03 (Damdama Kothi, 0.64 MLD) | 1 | 15000000 | 15000000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -04 (Nawabpura, 9.86 MLD) | 1 | 22500000 | 22500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -05 (Hathi wala Mandir, 4.09 MLD) | 1 | 15000000 | 15000000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -06 (Zama Masjid, 2.45 MLD) | 1 | 14500000 | 14500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -07 (Chandra Nagar, 4.34 MLD) | 1 | 17000000 | 17000000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -08 (Lajpat Nagar, 32.18 MLD) | 1 | 38500000 | 38500000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-3 IPS -09 (Baldevpuri, 1.88 MLD) | 1 | 16400000 | 16400000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-4 MPS -1 | 1 | 24700000 | 24700000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-4 MPS -2 | 1 | 17800000 | 17800000 | 0 | 0 | 0 | 1 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 150mm | 625 | 990 | 618750 | 0 | 0 | 0 | 625 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 200mm | 10 | 1290 | 12900 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 250mm | 570 | 1700 | 969000 | 0 | 0 | 0 | 570 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 300mm | 700 | 2100 | 1470000 | 0 | 0 | 0 | 700 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 350mm | 1650 | 2650 | 4372500 | 0 | 0 | 0 | 1650 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 400mm | 1150 | 3200 | 3680000 | 0 | 0 | 0 | 1150 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 450mm | 25 | 3700 | 92500 | 0 | 0 | 0 | 25 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 500mm | 25 | 4300 | 107500 | 0 | 0 | 0 | 25 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 600mm | 930 | 5650 | 5254500 | 0 | 0 | 0 | 930 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 700mm | 10 | 7700 | 77000 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM DI K7, pipe Supply 800mm | 10 | 10100 | 101000 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM PSC pipe 8kg/cm2, Supply900mm | 1270 | 9500 | 12065000 | 0 | 0 | 0 | 1270 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM PSC pipe 8kg/cm2, Supply1000mm | 10 | 11600 | 116000 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 150mm | 625 | 1040 | 650000 | 0 | 0 | 0 | 625 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 200mm | 10 | 1040 | 10400 | 0 | 0 | 0 | 10 | 0
Moradabad Zone | 15 | 21 Oct 2011 | Self Contracting | Ram Ganga Sewerage Project. | Pkg1,S.G-5 RM Carting & Laying of Pipe 250mm | 570 | 1040 | 592800 | 0 | 0 | 0 | 570 | 0